## Sheet1
Sprint Backlog Items | Tasks
As an election official, I want to be able to bring in multiple election files So that I can bring in different files from different balloting locations. | Bring in file names from command line Bring in file names from directory if no filename arguments
Acceptance Criteria: Multiple files are able to be selected
Definition of Done Unit tested Integrated into main system Documentation complete
Effort: Small
PBI Author(s) Tyler Grimm, Andrew Guerra
As an election official, I want to be able to process multiple IR election file headers correctly So that I can bring in different files from different balloting locations. | Read only one header from a set of files for an election
Acceptance Criteria: Multiple IR election headers are read
Definition of Done Unit tested Integrated into main system Documentation complete
Effort: Medium
PBI Author(s) Tyler Grimm, Andrew Guerra
As an election official, I want to be able to process ballots multiple IR election files So that I can bring in different files from different balloting locations. | Read in ballots for all files
Acceptance Criteria: IR ballots from all files are all read in
Definition of Done Unit tested Integrated into main system Documentation complete
Effort: Medium
PBI Author(s) Tyler Grimm, Andrew Guerra
As an election official, I want to be able to process in multiple CPL election file headers correctly So that I can bring in different files from different balloting locations. | Read only one header from a set of files for an election
Acceptance Criteria: Multiple CPL election headers are read
Definition of Done Unit tested Integrated into main system Documentation complete
Effort: Medium
PBI Author(s) Tyler Grimm, Andrew Guerra
As an election official, I want to be able to process ballots multiple CPL election files So that I can bring in different files from different balloting locations. | Read ballots in a loop
Acceptance Criteria: CPL ballots from all files are all read in
Definition of Done Unit tested Integrated into main system Documentation complete
Effort: Medium
PBI Author(s) Tyler Grimm, Andrew Guerra
As an election official I want to see a table displaying the round(s) of an IRV election in the listed format So that I can see how the election progressed | Create election progression data collection singleton Integrate singleton into IR election Display contents of singleton to GUI table
Acceptance Criteria: The table displays progression of the election
Definition of Done Unit tested Integrated into main system Documentation complete
Effort: Large
PBI Author(s) Andrew Guerra
As an election official, I want to be able to process a PO election file header So that I can run a PO election | Create parser for PO election header Integrate parser into system
Acceptance Criteria: PO election headers are read in Provided PO election header format is handled
Definition of Done Unit tested Integrated into main system Documentation complete
Effort: Medium
PBI Author(s) Tyler Grimm, Andrew Guerra
As an election official, I want to be able to process ballots in a PO election file So that I can run a PO election | Create PO ballot class Create parser for PO ballots Integrate ballot parser into system
Acceptance Criteria: PO election ballots are read in Provided PO election ballot format is handled
Definition of Done Unit tested Integrated into main system Documentation complete
Effort: Medium
PBI Author(s) Tyler Grimm, Andrew Guerra
As an election official, I want to be able to process in multiple PO election file headers correctly So that I can bring in different files from different balloting locations. | Read only one header from a set of files for an election
Acceptance Criteria: Multiple PO election headers are read in
Definition of Done Unit tested Integrated into main system Documentation complete
Effort: Medium
PBI Author(s) Tyler Grimm, Andrew Guerra
As an election official, I want to be able to process ballots in multiple PO election files So that I can bring in different files from different balloting locations | Read in ballots for all files
Acceptance Criteria: PO ballots from all files are all read in
Definition of Done Unit tested Integrated into main system Documentation complete
Effort: Medium
PBI Author(s) Tyler Grimm, Andrew Guerra
As an election official I want to run a PO election So that a winner of a PO election can be determined | Implement PO algorithim in run Integrate run into system
Acceptance Criteria: PO election winner is determined by candidate that has a plurality of votes
Definition of Done Unit tested Integrated into main system Documentation complete
Effort: Medium
PBI Author(s): Hady Kotifani, Andrew Guerra
As an election official, I want to be break ties in a PO election via a coin toss So that I can resolve ties fairly. | Implement tie break in PO algorithim in run
Acceptance Criteria: A winner can be determined from a coin toss
Definition of Done Unit tested Integrated into main system Documentation complete
Effort: Small
PBI Author(s) Tyler Grimm, Andrew Guerra
As an election official I want to display stats of a PO election to the screen with percentages of each candidate So that constituents who voted know how well their candidate did in the election | Calculate stats for election Display stats to terminal
Acceptance Criteria: PO election stats are calculated PO election stats for election are displayed
Definition of Done Unit tested Integrated into main system Documentation complete
Effort: Small
PBI Author(s): Hady Kotifani, Andrew Guerra