## Sheet1
Sprint Backlog Items | Tasks
As an election official, I want to be able to bring in multiple election files So that I can bring in different files from different balloting locations. | Bring in file names from command line Add make file functionality with multiple files Create Unit Tests for confirmation of function Write documentation Add test specification fuctionality in makefile
Acceptance Criteria: Multiple files are able to be selected
Definition of Done Unit tested Integrated into main system Documentation complete
Effort: Small
PBI Author(s) Tyler Grimm, Andrew Guerra
As an election official, I want to be able to process multiple IR election file headers correctly So that I can bring in different files from different balloting locations. | Read only one header from a set of files for an election Allow function to take more than one file Create Unit Tests for confirmation of function
Acceptance Criteria: Multiple IR election headers are read
Definition of Done Unit tested Integrated into main system Documentation complete
Effort: Medium
PBI Author(s) Tyler Grimm, Andrew Guerra
As an election official, I want to be able to process ballots multiple IR election files So that I can bring in different files from different balloting locations. | Read in ballots for all files Allow function to take in more than one file Create Unit Tests for confirmation of function Create System Testing for confirmation of function
Acceptance Criteria: IR ballots from all files are all read in
Definition of Done Unit tested Integrated into main system Documentation complete
Effort: Medium
PBI Author(s) Tyler Grimm, Andrew Guerra
As an election official, I want to be able to process in multiple CPL election file headers correctly So that I can bring in different files from different balloting locations. | Read only one header from a set of files for an election Create helper function to move Scanners to read in ballots Modify Election to hold Array of Scanner objects Add Unit testing
Acceptance Criteria: Multiple CPL election headers are read
Definition of Done Unit tested Integrated into main system Documentation complete
Effort: Medium
PBI Author(s) Tyler Grimm, Andrew Guerra
As an election official, I want to be able to process ballots multiple CPL election files So that I can bring in different files from different balloting locations. | Create an array of Scanner objects in Main for Elections Incorporate looping to iterate through .csv files to read in ballots and calculate total ballots in election Unit testing
Acceptance Criteria: CPL ballots from all files are all read in
Definition of Done Unit tested Integrated into main system Documentation complete
Effort: Medium
PBI Author(s) Tyler Grimm, Andrew Guerra
As an election official I want to see a table displaying the round(s) of an IRV election in the listed format So that I can see how the election progressed | Create election progression data collection singleton Integrate singleton into IR election Display contents of singleton to GUI table Do unit testing Do system testing
Acceptance Criteria: The table displays progression of the election
Definition of Done Unit tested Integrated into main system Documentation complete
Effort: Large
PBI Author(s) Andrew Guerra
As an election official, I want to be able to process a PO election file header So that I can run a PO election | Create parser for PO election header Integrate parser into system create unit tests
Acceptance Criteria: PO election headers are read in Provided PO election header format is handled
Definition of Done Unit tested Integrated into main system Documentation complete
Effort: Medium
PBI Author(s) Tyler Grimm, Andrew Guerra
As an election official, I want to be able to process ballots in a PO election file So that I can run a PO election | Create PO ballot class Create parser for PO ballots Integrate ballot parser into system Create unit test for the system
Acceptance Criteria: PO election ballots are read in Provided PO election ballot format is handled
Definition of Done Unit tested Integrated into main system Documentation complete
Effort: Medium
PBI Author(s) Tyler Grimm, Andrew Guerra
As an election official, I want to be able to process in multiple PO election file headers correctly So that I can bring in different files from different balloting locations. | Read only one header from a set of files for an election Implement unit tests
Acceptance Criteria: Multiple PO election headers are read in
Definition of Done Unit tested Integrated into main system Documentation complete
Effort: Medium
PBI Author(s) Tyler Grimm, Andrew Guerra
As an election official, I want to be able to process ballots in multiple PO election files So that I can bring in different files from different balloting locations | Read in ballots for all files Create unit test
Acceptance Criteria: PO ballots from all files are all read in
Definition of Done Unit tested Integrated into main system Documentation complete
Effort: Medium
PBI Author(s) Tyler Grimm, Andrew Guerra
As an election official I want to run a PO election So that a winner of a PO election can be determined | Implement PO algorithm in run Integrate run into system Create Unit Tests Create system tests for integration
Acceptance Criteria: PO election winner is determined by candidate that has a plurality of votes
Definition of Done Unit tested Integrated into main system Documentation complete
Effort: Medium
PBI Author(s): Hady Kotifani, Andrew Guerra
As an election official, I want to be break ties in a PO election via a coin toss So that I can resolve ties fairly. | Implement tie break in PO algorithm in run Create unit test Create system tests
Acceptance Criteria: A winner can be determined from a coin toss
Definition of Done Unit tested Integrated into main system Documentation complete
Effort: Small
PBI Author(s) Tyler Grimm, Andrew Guerra
As an election official I want to display stats of a PO election to the screen with percentages of each candidate So that constituents who voted know how well their candidate did in the election | Calculate stats for election Display stats to terminal Create unit tests Create system tests
Acceptance Criteria: PO election stats are calculated PO election stats for election are displayed
Definition of Done Unit tested Integrated into main system Documentation complete
Effort: Small
PBI Author(s): Hady Kotifani, Andrew Guerra